## Sheet1
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
SprintSync Frontend | Project Initialization & Setup | 1 | 2 |  | Vite + React + TypeScript setup with basic configuration
SprintSync Frontend | UI Component Library Creation | 3 | 5 |  | Button, Input, Modal, and other reusable components
SprintSync Frontend | Authentication System Implementation | 4 | 6 |  | Login/Register forms with validation and state management
SprintSync Frontend | Layout & Navigation System | 2 | 4 |  | Main layout with header, navigation, and responsive design
SprintSync Frontend | State Management Setup | 2 | 3 |  | Zustand store for auth and React Query for API state
SprintSync Frontend | API Client & Services Integration | 3 | 5 |  | Axios client with interceptors and service layer
SprintSync Frontend | Dashboard Implementation | 4 | 7 |  | Statistics, charts, task overview and activity visualization
SprintSync Frontend | Task Management Interface | 5 | 8 |  | Task list view with CRUD operations and status management
SprintSync Frontend | Kanban Board Implementation | 4 | 6 |  | Drag-and-drop kanban board with visual task management
SprintSync Frontend | AI Integration for Task Suggestions | 3 | 5 |  | Groq API integration for AI-generated task descriptions
SprintSync Frontend | Responsive Design & Styling | 4 | 7 |  | Mobile-responsive design with CSS modules and variables
SprintSync Frontend | Error Handling & Loading States | 2 | 4 |  | Global error handling, loading spinners, and user feedback
SprintSync Frontend | Testing Setup & Deployment Config | 2 | 3 |  | Build optimization, production deployment configuration